## Sheet1
Number | Description | Currently on Project board | To be approved or closed | Launch (mid July) | Go-live (mid Aug) | Fall patch | Later | Frank's comments
889 | Update sticky note for SIZE Quota |  | X |  |  |  |  | Will take a look. Should be easy.
843 | User guides documentation (in progress) |  | X
907 | Submission List Query broken after changing logic on filter to "AND" (bug) (in progress) (question) | X | X
1023 | triptych errors on occasion(bug) (in progress) |  | X
1104 | Student Needs Correction View - confirmation message or note next | X | X
1105 | Metadata_thesis file in DSpace Simple Archive export needs corrections (review) |  | X
1127 | initial package build of Vireo 4.x doesn't copy application.yaml into war file |  | X |  |  |  |  | I'll look into it but believe jar deploy is preferable and had not encountered problems with jar deploy. SL moved to LATER
1146 | Search box failing | X | X
1150 | Batch comment to be revisted | X | X
1156 | View Submission hangs following an export. (review) |  | X
1157 | Please Report' 500 error says an error report has been submitted but clicking OK results in no action (modal stays open) (Community Sprint)(next) | X | X
1162 | Change the "Degree Date" to "Graduation Semester" in List Views | X | X
1189 | Metadata_thesis.xml in DSpace Simple export missing degree values (review) |  | X
1191 | Dublin_core.xml in DSpaceSimple export missing dates for provenance fields (in progress) |  | X
1223 | Error Message : Destination is out of range | X | X
1236 | Change metadata keys next | X | X |  |  |  |  | Needs to be fixed
1242 | CVs no longer updating | X | X
840 | Update README documentation (next) | X |  | X |  |  |  | Needs to be done. Corresponds with 1158
842 | Code comments and JavaDocs development documentation |  |  | X |  |  |  | Needs to be done. Corresponds with 1158
1158 | Test Vireo 4 deployment documentation |  |  | X |  |  |  | Current docs and pom.xml are set for war deploy. // jar deploy is more direct and worth adding
1190 | Dublin_core.xml in DSpaceSimple export missing value of dc.date.issued |  |  | X |  |  |  | Will take a look.
1200 | Add functionality to Remove All | X |  | X |  |  |  | Any alternatives? SL: if this one is difficult or costly, let's not fix it at all. It would only be of value on initial set up.
1231 | Add Vireo 3 functionality to batch email Advisors (see 1272) | X |  | X |  |  |  | Needs to be fixed
1260 | Remove dc.date.issued from Defense Date Field Profile |  |  | X
1269 | Update of Embargo Type results in 500 (bug) |  |  | X |  |  |  | Needs to be fixed
1272 | (batch) e-mail sending fails if any Assignee is invalid (see 2131) |  |  | X |  |  |  | Needs to be fixed
712 | MARC21 export feature review |  |  |  | X
839 | Develop migration strategy for 3.x to 4.x development feature |  |  |  | X
1121 | Truncate Last Action content in View |  |  |  | X
1140 | ProQuest export is broken bug next | X |  |  | X
1151 | Add placeholders to email fields in Add Comment and Add File |  |  |  | X
1176 | SubmissionController.java DSpaceSimple catch block does nothing useful but obscure errors | X |  |  | X? |  |  | More useful for devs than users but easy to fix. SL moved to GO Live, but uncertain.
1225 | Add Graduation Semester to email template variables next | X |  |  | X
1247 | BUG - Unable to change Embargo in View submission |  |  |  | X
1275 | The e-mail templates are not substituting the variables in the subject line for the e-mail. |  |  |  | X
1279 | Unable to delete file type due to restrictions, despite the file type not being used |  |  |  | X
771 | As an Admin, I require human-readable glosses to create my email templatesenhancement question story |  |  |  |  | X
841 | Code cleanup and formatting development |  |  |  |  | X?
1174 | Improve feedback for editing default email templates |  |  |  |  | X
1184 | Change "true" values to "yes" in Excel export |  |  |  |  | X
1221 | Custom Actions do not export correctly in Excel |  |  |  |  | X
1227 | Using clear button in datepicker for input-datetime causes field duplication (disappears when page is refreshed) |  |  |  |  | X
1235 | mixed content delivered by vireo4 not rendered under https in certain browsers |  |  |  |  | X
1264 | BUG: Public display of filters is not working |  |  |  |  | X
1265 | Update text in Save Current Filter |  |  |  |  | X
1266 | User Preferences are not saved in Profile |  |  |  |  | X
1107 | Java 10 compatibility? | [5 empty] | ?
721 | Organizations not deleting in some circumstances bug icebox | [5 empty] | X
731 | UI shows validation error (unique key of name) when renaming WS to name of it's originating WS bug question. SL: Resolved with screen refresh. | [5 empty] | X
732 | Once WS at institution level is marked No for override, it cannot be changed back bugicebox | [5 empty] | X
765 | Unable to refresh basic login token if using remote authentication service bugenhancement | [5 empty] | X
769 | As a manager, I would like to specify export mappings per organization per export.enhancement feature story | [5 empty] | X
800 | As a user, I would like to be able to change my password feature story | [5 empty] | X
812 | FieldProfile and Note database constraints need to be strengthened enhancement | [5 empty] | X
817 | Clear query params on navigation bug in progress | [5 empty] | X
827 | Combine request for file upload/replace and save associated field value enhancementicebox | [5 empty] | X
935 | The craftDynamicSubmissionQuery() method may not be generating the query as intended bug icebox | [5 empty] | X
1009 | admin submission view file upload not able to upload newly create document typesbacklog bug enhancement | [5 empty] | X
1122 | Introduce a distinction between Status and State enhancement | [5 empty] | X
1123 | Allow for CRUD of Statuses feature | [5 empty] | X
1131 | Handle request for non-existent submission (/admin/view) bug | [5 empty] | X
1183 | Apply email validation to addFileModal enhancement | [5 empty] | X
1214 | Upload CV needs better feedback than a 500 when it fails | [5 empty] | X
1215 | After deleting CV, clear edit form below (SL: unable to reproduce) | [5 empty] | X
1216 | Delete submission not persisting (SL: unable to reproduce) | [5 empty] | X
1218 | Change default recipient for SYSTEM Initial Submission rule | [5 empty] | X
1219 | Update URL in SYSTEM Initial Submission email template | [5 empty] | X
1220 | Second "SUBMISSION_URL" | [5 empty] | X
1224 | email templates | [5 empty] | X
1226 | Add info text to ProQuest Settings indexing setting | [5 empty] | X
1233 | A deleted field profile cannot be recreated | X |  |  |  |  | X
1248 | Do not require email for Input type INPUT_CONTACT feature | [5 empty] | X
1251 | Cannot get Vireo 4 started with MySQL database | [5 empty] | X
1267 | Issue saving organization when multiple users are using attempting the same action concurrently bug | [5 empty] | X
1270 | Add Alt-text missing in on screen editor of controlled vocabularies | [5 empty] | X
1271 | Admin Settings -> Application Settings -> Submission Availability has "todo" in help | [5 empty] | X
1273 | Feature Request: E-mail forms (comment and comment/batch forms) should only add e-mail once | [5 empty] | X
1277 | Seemingly refreshing entire page on Manage Workflow Settings | [5 empty] | X
1278 | Organization Category Settings fails to add after Drag and Drop attempt (can be resolved with page refresh) | [5 empty] | X
745 | Karma UI Test Coverage testing | [6 empty] | Need to check in with Kevin Day to see where this is at. Does it need to be a release priority?
746 | Protractor end-to-end Test Coverage testing
1274 | Configuration e-mail from address might not be used
1276 | Potential Aria-hidden accessibility issue with reportModal

## Completed
Approved and Closed
Number | Description
1103 | Change default text for committee members